# EUDR Practicalities: A Fast Track BIC Project

The book industry’s supply chain organisation

UK & Ireland

Contents

Purpose of the Document	3

Purpose of the Project	3

Summary of Changes to EUDR since the original BIC Guidance was published on 15 August 2025	4

Methodology	4

Roles	4

First Operators	4

Downstream Operator	5

Non-EU Operator	5

Examples of Above Roles in Action	5

The DDS and the Data	6

The Task and Finish Working Group (T&FWG)	8

Deliverables	9

Executive Summary	9

Recommendations	10

# Purpose of the Document

The purpose of this document is to provide the reader with an introduction to the EUDR Practicalities: A Fast Track BIC Project. It is the first document that the reader should read, as it provides an overview of the whole project and an introduction to the other deliverables provided as a whole package to help navigate The European Union Deforestation Regulation (EUDR).

The document provides a brief introduction to EUDR and the commodities covered under the regulation since the 12-month delay announced by the EU Parliament and Council in December 2025 and the subsequent follow up report issued by the EU Commission on 4 May 2026.  It explains that EUDR is about due diligence in the supply chain to make sure the commodities covered by the regulation are not causing deforestation or land degradation. It touches on the implementation of EUDR and the EU due diligence system - EU Traces. It points the reader to BIC’s EUDR Helpful Information document that explains various requirements of the regulation, and the EUDR data flow maps that BIC has produced.

For any organisation, the importance of thoroughly researching what is going on in the supply chain with regards to data flows, responsibilities, and the need to seek legal advice should be noted by the reader.

This document has been updated considering the changes to EUDR, that is the removal of Chapter 49 (Printed Material) from the regulation. Chapter 49 covers printed matter such as books and scientific journals.

# Purpose of the Project

The aim of this BIC project is to provide the book industry supply chain with practical guidance on how to implement the European Union Deforestation Regulation (EUDR). The EUDR regulation requires seven commodities (cocoa, coffee, soy, palm oil, wood, rubber, and cattle, and their derivatives) to be deforestation or forest and land degradation free before they can be imported or exported in the EU. Part of the process requires that organisations undertake a due diligence review of their supply chains. For the timber industry and its derivative products this means tracing back to the geolocation upon which the trees grew.

The outcomes from the in-person April 2025 BIC EUDR Workshop were the starting point of the project. This workshop hosted 35 participants from 22 different organisations. The challenge was to find consensus on how to move forward as various people and organisations had different understandings of the regulation. Since then, the 2025 project group grew to 41 active members. This has subsequently been reduced to around 25 members for whom the regulation is still relevant. The members who no longer work on the project only produce Chapter 49 product.

It is also a changing landscape with the EU Commission still to make decisions on various aspects of the regulation, such as how non-EU Operators will gain access to EU Traces, what data will be available in the whole book industry supply chain, and how the re-importing of goods process will work. Information about these issues is expected in September 2026. EU Traces is the EU system that allows organisations to declare that due diligence has been performed before the import, export, domestic production or merchandising of products that are in scope of EUDR. The level of risk associated with each country will impact the level of due diligence required by organisations in the supply chain.

# Summary of Changes to EUDR since the original BIC Guidance was published on 15 August 2025

- The EU Parliament and Council approved another year’s delay to the implementation of EUDR at the end of 2025 until 30 December 2026.

- They also charged the EU Commission with investigating and reporting back on how the regulation could be simplified.

- At the same time, it was argued by the Internation Publishers Association, the European and International Booksellers Association along with other European organisations that printed matter (books and scientific journals) was not a commodity, but a resource and should therefore be exempt from the regulation. At the same time the EU Council and Parliament approved the delay of the implementation of EUDR until 30 December 2026 they also decided that all products which fall into Chapter 49 are exempt.

- Chapter 48 products are still covered by EUDR such as (but not limited to) notebooks and diaries.

# Methodology

For BIC the book industry supply chain covers organisations and trade bodies from the author to the book seller. The original 2025 Task and Finish Working Group (T&FWG) for this project had 34 members participating from across 19 organisations in the book Industry supply chain.

Under EUDR the responsibility for creating the Due Diligence Statement (DDS) lies with the EU customer/importer of record who first places the goods on the market. A DDS is the statement created in EU Traces that contains the geolocation and species data of the trees used to make the imported pulp or paper made in the EU.

## Roles

The simplified 2026 version of EUDR has changed 1) responsibilities in the supply chain and 2) what organisations are required to now do.

### First Operators

First Operators are the EU organisations that first place the goods on the EU market.

- They are still required to create DDSs and pass the reference and verification number or declaration identifier down the supply chain

- They must hold the DDS data for 5 years

- They must conduct risk assessments of their supply chain (simplified for low-risk countries)

- They must conduct risk mitigation of their supply chain (low-risk countries are exempt)

### Downstream Operator

- They are the next operator in the supply chain after the First Operator and transform relevant products into another relevant product

- No new due diligence and no new DDS required, but they must hold any data they do receive for 5 years

- There remains a requirement to register with EU Traces in order to:

  - Collect information on upstream operators – DDS number or declaration identifier only if their supplier is a first operator

  - A declaration identifier is created after a simplified declaration (SD) is submitted by micro or small primary operators (MSPOs). This is part of the EUDR simplification for MSPOs that they are not required to perform the same amount of due diligence as larger organisations.

- Required information by the Downstream Operator – their own organisation’s name, registered trade name or registered trademark, postal address, email address and if available a web address

### Non-EU Operator

The EU has created a new Operator known as a Non-EU Operator. The role of the Non-EU Operator is to create an importing product DDS if they are the importer of record placing the goods on the EU market. Additionally, the

- Non-EU Operator then has to pass all the raw data they have used to create this importing product DDS to the first EU Operator in the supply chain.

- The EU First Operator then has to create their own separate DDS for the product that has been imported to the EU.

## Examples of Above Roles in Action

Below are some examples from the book industry supply chain, following the basic principle: it doesn’t matter what you are – it’s what you do!

The book industry supply chain needs to ensure that all organisations across the supply chain know what the commodity code of a product is. This is especially true for printers as they are still obligated to hold information for products in Chapter 48.

Example 1 – Starting point: EU Paper Mill

- In this example the paper mill is the First Operator – they have to submit a pulp DDS and pass the DDS number on to:

- EU paper manufacturer (who in this example is a First Downstream Operator) – they have to collect the DDS information on the pulp that they purchase and keep it for five years. The EU paper manufacturer may or may not pass the pulp DDS information down the supply chain, as they have no obligation to do so under EUDR

- EU printer is a Downstream Operator for paper, as they buy paper. They may or may not receive a DDS covering the pulp from the EU paper manufacturer. Their role is to make an assessment of the paper they are purchasing to ensure it complies with EUDR.

This is relevant for all paper and pulp being placed on the EU market as that will always be covered by EUDR.

Example 2 – Starting point: UK Printer

- In this example the UK printer will need to know if they are printing a Chapter 48 or 49 product, this information needs to come from the publisher

- If a Chapter 48 product is being produced, then they must collect all the relevant geolocation and tree species data and even paper DDS information (if available) that they can. They will need to pass all of this information to either the Non-EU Operator or EU Operator to create the product DDS so the goods can be placed on the EU market

- Paper exported from the EU to a UK printer no longer comes with a DDS. In such cases the UK printers need to keep good records of all the purchase orders, invoices and delivery notes on all the paper they have purchased from the EU. This is so they have an audit trail on all the papers they have bought from the EU should the need arise to prove the paper originated in the EU as the export of paper from the EU no longer has a DDS with the export

- Any data that they collect will need to be stored for 5 years

- If a Chapter 49 product is being produced then that product is exempt from EUDR

Example 3 – Starting point:  Printer in the Rest of the World (i.e. non-UK and non-EU)

- In this example the printer will need to know if they are printing a Chapter 48 or 49 products

- If Chapter 48 product is being produced then the printer must collect all the relevant geolocation and tree species data that they can and pass it to either/both the Non-EU Operator or EU Operator (as applicable) to create the product DDS so the goods can be placed on the EU market depending upon the route of supply if the goods are going directly to the EU first or not

- Any data that they collect will need to be stored for 5 years

- If a Chapter 49 product is being produced then that product is exempt from EUDR

NOTE

- The route of supply of data still needs to establish as to how the geolocation data and tree species information will be passed down the supply chain if organisations actually have access to it. The proportion of products falling under the revised regulation is so much smaller now that printed matter (Chapter 49) has been removed. All organisations in the supply chain will need accurate record keeping should the need arise to prove they have the required data for Chapter 48 products. As well as being able to prove that a product falls under Chapter 49 and is therefore exempt from EUDR.

- Advice is also needed from the EU about how to reimport goods that originally have been exported from the EU. The EU has said that a new TARIC code will be created along with a dummy DDS so Chapter 48 goods can be reimported to the EU.

# The DDS and the Data

Under EUDR the responsibility for creating the Due Diligence Statement (DDS) lies with the EU customer/importer of record who first places the goods on the market. This is the First Operator role in EU Traces.

A DDS is the statement created in EU Traces that contains the geolocation and species data of the trees used to first make the pulp and then the paper used to make the Chapter 48 products and can be used to verify that no deforestation or land degradation has taken place.

So, in theory UK organisations should only need to pass the required geolocation and tree species data down the supply chain. This data may take the form of a DDS for papers that are produced in the EU or geolocation data and tree species information in GeoJSON file format and tree species information.

The importing EU entity would then use this data to create the product DDS. The product DDS needs to be created by the EU customer/importer of record so that the competent authorities, responsible for auditing EUDR, can check that product is compliant with the regulation. These competent authorities do not have jurisdiction to audit countries outside the EU.

Printers need to record all the paper DDSs (if they have them or the geolocation data) used in a book's manufacture. A new DDS for the product is required because the commodity code changes from paper (Chapter 47) to a Chapter 48 product.

The EU Commission has also stated that small foresters now need to provide a post code and not a GeoJSON file for the geolocation of the trees. At the time of writing, clarification of how this will work in EU Traces is yet to be established.

UK organisations, as they are not in the EU, have the responsibility to pass information down the supply chain for Chapter 48 products. This information can take two forms.

- The first being any DDS data they have or more likely the re-importing DDS number and corresponding TARIC code for goods that have already been on the EU market.

- The second is the basic raw data (geolocation and tree species). This raw data could either be a DDS from paper mills in the EU or geolocation and tree species data from mills outside the EU. This raw data would then be used by either the Non-EU Operator and/or First EU Operator whomever is placing the goods on the EU market to create a Chapter 48 product DDS. If the Non-EU Operator places the goods on the marker for customs purposes to enable the goods to cross the border, then the First EU Operator will also have to create a Chapter 48 product DDS when they place the goods on the EU market.

The T&FWG felt many EU customers would want to see a DDS in the Chapter 48 product’s metadata feeds before they would place an order for Chapter 48 products. During the project increased evidence has come to light to suggest that this was indeed a correct assumption. Also, some distributors and warehouses in the UK are of the opinion that if a Chapter 48 product did not have a DDS associated with it when it arrived with them, then the product would simply be market restricted for sale in the EU until there was one. Due to the large amounts of data associated with the GeoJSON files and tree species data just for one product distributors and warehouses do not know how they would manage the data for all the Chapter 48 products they hold. The issue of passing data down the supply chain has been mentioned before. The T&FWG’s understanding has not changed on this point.

# The Task and Finish Working Group (T&FWG)

To begin the project, the T&FWG reviewed the eight data flow maps that were created for the April 2025 EUDR Workshop. It was decided that not all 34 of the T&FWG members needed to discuss the maps going forward, so two subgroups were created. The members of the T&FWG then volunteered for which group they wanted to be in. One subgroup looked at the general supply of books and corresponding data, and the other focussed on print on demand (POD). This was then reduced to one group that reviewed the maps when the project restarted in May 2026 once the EU Commission had published its simplification to the regulation.

The full T&FWG met every week to discuss progress of the overall project. Members would feedback information that they had learnt during the week, and there would be a general discussion around other EUDR topics such how organisations would pass the data through the supply chain and the transition period. The frequency of the full team meeting was changed to monthly when the project re-started in May 2026.

The two subgroups also each met once a week. To begin with the subgroups would discuss the data flow maps and refine the various data flows. The project manager would then update the maps and circulate them for review at the next weekly meeting. This process continued until consensus was reached and the maps finalised. In the end the original eight maps were reduced to three and a new POD map was created. These maps are currently being reviewed in light of the changes to EUDR. In light of the 2026 changes to EUDR, the T&FWG has agreed that the POD map will not be required going forwards.

One premise behind those maps was that it might be desirable for a DDS to be created as early as possible in the process. This is now not possible due to the fact it is not possible to nest DDSs within themselves anymore. A book DDS is required to import goods into the EU to prove that they are made from wood derived materials which are deforestation and land degradation free. There could be various DDSs for the EU papers or raw data for non-EU papers used in the printing of books. Once the paper(s) has been turned into a book, a new book DDS is required as the commodity code has changed from paper to book. For books being produced under a POD model it has been assumed that these will be Chapter 49 product and therefore exempt from EUDR. If a product is produced as POD under Chapter 48 it is most likely to be a personalised item and therefore be a B2C transaction and exempt from EUDR.

Once the subgroups had approved the new data flow maps their attention turned to other questions regarding EUDR such as:

- the transition period and

- access to EU Traces (the EU system that generates the DDS).

The EU Commission has designated a transition period which covers product produced between the 29 June 2023 and the 30 December 2026. Any product produced before 29 June 2023 only must comply with the existing EUTR regulation until 31 December 2028 before it then falls under the EUDR regulation. Product produced between the 29 June 2023 and 30 December 2026 falls under the requirements of EUDR. This is a complex topic that is covered in the BIC EUDR Practicalities - Helpful Information document. Each subgroup provided a short update.

In the case of access to EU Traces a solution has been found for UK Non-EU Operators.

The transition period is much more complicated, with an understanding that has been reached by the T&FWG, but a full solution is yet to be reached. The transition period remains in place for products that fall under Chapter 48, but not those in Chapter 49.

The current solutions to help organisations navigate EUDR are detailed in the Helpful Information document as part of the deliverables for this project.

# Deliverables

The deliverables for this project are:

- A final report with Executive Summary and recommendations,

- A Helpful Information document for the reader to navigate EUDR with suggestions on what they need to do to be compliant. This document covers:

  - Introduction

  - European Union Deforestation Regulation (EUDR)

  - Access to EU Traces

  - How to create a Due Diligence Statement (DDS)

  - Data maps and explanations

  - Information on what EUDR data Chinese mills can provide

  - Information on what EUDR data US mills can provide

  - Information on what EUDR data Indian printers provide

  - Shipping requirements, documentation and specific EUDR TARIC codes

  - Help with understanding the transition period

  - Risk assessment document for stock currently in warehouses

  - Risk assessment documentation

  - Glossary

- Three data flow maps, for the reader to understand how that flows through the supply chain and is different from the flow of product. These maps are:

  - Product printed in the UK on EU paper

  - Product from ROW to the UK

  - Product from ROW to EU Customer

- A set of FAQs

# Executive Summary

The aim of this project was to provide the book industry supply chain with practical guidance on how to navigate EUDR and what an organisation needs to consider. To that end the original project and the subsequent project in light of the changes have both delivered. The T&FWG has gathered a lot of useful information together and through robust conversations come to a consensus on the ideal way the EUDR could be implemented. It must be acknowledged that not all organisations will follow the ideal path as they have no obligations under EUDR as they are located in a non-EU country.

There are different approaches that organisations can take to implement the regulation, with large organisations opting for an external organisation (such as Live-EO and osapiens). In light of the simplification to EUDR the use of these external organisations has changed, but they still offer a service to the book industry supply chain should someone want to use them. This could create a two-tier solution to managing EUDR, so it is important that BIC continues to help the book industry supply chain, especially SMEs.

# Recommendations

Our understanding of EUDR is evolving with time, especially when the EU Commission updates their FAQs. Therefore, going forward the T&FWG would recommend:

- BIC continues to monitor the implementation of EUDR to provide further and updated guidance to the book industry supply chain in order to help reach consensus on working together,

- Organisations need to take their own legal advice,

- Organisations need to look both one up and one down from themselves in the supply chain to see how their suppliers/customers are handling the regulation and work with them,

- Organisations need to work out how they are going to conduct risk assessments of their supply chains, if they have not done so already,

- Publishers need to conduct a risk assessment into the Chapter 48 stock that they currently hold during the transition period. This stock might not be compliant with EUDR and therefore cannot be sold into the EU,

- Publishers need to find a way to tell printers if a product has a commodity code of 48 or 49, This information could be provided on the PO sent to the printers,

- Publishers or organisations with a large proportion of their work in commodity code 48 would be advised to talk to their printers on how they could manage this,

Report prepared by: Simon Crump, BIC Environmental Consultant

EUDR Practicalities: A Fast Track BIC Project

BIC would like to thank the T&FWG members who participated and who represented the following organisations:

Bloomsbury

Bonnier Books

BooksoniX

C & C Offset Printing Co (UK)

Canongate

Clays

CPI

EDItEUR

HarperCollins

Hewson Books

Hobbs

Macmillan

Nielsen BookDataNIQ

Publiship

Sage

Star Book Sales

Taylor & Francis

Thames & Hudson

Waterstones

Updated August 2026

© Book Industry Communication 2026 All Rights Reserved